## Slide 1
Promoting Regional Development by building the capacity of the VET system

## Slide 2
Creating and applying an action plan

## Slide 3
Disclaimer
The European Commission support for the production of this publication does not constitute an endorsement of the contents which reflects the views only of the authors, and the Commission cannot be held responsible for any use which may be made of the information contained therein.
Project Nº: 2021-1-RO01-KA220-VET-000028118

## Slide 4
Consortium

## Slide 5
Contents
01
02
03
04
06
05
07
Definition of an Action Plan
Why do you need an Action Plan?
An Action Plan for regional development
Examples of Regional development Action Plans
Steps to develop an Action Plan
Key elements of an Action Plan
Unit summary

## Slide 6
“
He who fails to plan is planning to fail
Winston Churchill

## Slide 7
At the end of this unit, you will be able to create and apply an Action Plan
KNOWLEDGE | SKILLS | COMPETENCES
Understand what an Action Plan is Understand the benefits of Creating an Action Plan Understand the Key Elements of an Action Plan | Write an action plan Visualize the Action Plan | Creating, implementing, and monitoring the tasks related with the Action plan

## Slide 8
An action plan is a list of action items and resources needed to achieve project goals and objectives.
It can be considered as a visual representation of the timeline, a list of tasks, agents responsible for each of them and a follow-up of their progress to come up with the best results.
This document can help plan and monitor activities, identify the resources needed, and how and when they should be used to ultimately achieve the stated result.
Definition of an Action Plan
Steps
Resources
Goals
ACTION PLAN

## Slide 9
Offline Activity 1
The most important ingredients you need to create an effective action plan are the goals you want to achieve. Since you are an EERD, you might have already defined goals related to regional development, haven’t you?

## Slide 10
An Action Plan for regional development
Regional Action Plan
It translates strategies into annual workplans, mobilises resources for activities, assigns roles and responsibilities of stakeholders, and contains a monitoring plan to track progress.
Annual workplans
Strategies
Resources
Assets, funding, human resources
Roles and responsibilities
Monitoring plan
To track progress

## Slide 11
Why do you need an Action Plan?
clarifies what resources you’ll need to reach your regional development goals
represents a timeline for the action items
determines what team agents you’ll need to hold each task
helps order project tasks in a sequential and timely manner to achieve the specified objectives
helps track progress and measure project performance
maximizes agent productivity and resource allocation
prepares you for predictable and preventable challenges and helps you focus your resources to achieve your main goals
Generates a goal-driven workflow, so you know what to work on throughout the project
An Action Plan clarifies goals to be achieved, teams and service providers to involve, tasks, milestones, and resources needed to complete the project.

## Slide 12
Key elements of an Action Plan
A specific description of the aimed goal (SMART)
Tasks or action items and corresponding deadlines and timeline to reach the stated goal
Agents who will be responsible for each action item
Resources needed to complete the action items
Measures to evaluate progress

## Slide 13
Offline Activity 2
Remember that your regional Action Plan is not definitive. You should be able to adjust it as your regions needs change in time or evolve.

## Slide 14
Steps to develop an Action Plan
Step 1- Define your goal
Step 2 - List tasks
Step 3 - Prioritise tasks
Step 4 - Assign tasks
Step 5 - Assess and improve

## Slide 15
Steps to develop an Action Plan
Step 1- Define your goal
Be specific with your Action Plan goals. Define where your region is and where you want it to be. If there are alternative ways to achieve your Action Plan goal, evaluate your situation and choose the best opportunities to succeed, depending on your available resources.
SPECIFIC
MEASURABLE
ACHIEVABLE
RELEVANT
TIME-BASED
SMART is an acronym that indicates how to set ideal goals and objectives in an Action Plan. Your regional goals should always be “SMART,” which stands for specific, measurable, achievable, relevant and time-based.
These characteristics define the guidelines to help Action Plans be more effective, while ensuring agents always pursue their assigned goals.
Goals allow agents to focus on their roles and responsibilities, in order to successfully complete their action items.

## Slide 16
Offline Activity 3
Now that SMART is defined, how do you write SMART goals? The process starts with asking a lot of questions to yourself, your team and involved stakeholders. The answers to these questions will help sharpen your strategy and goals will become clear and attainable.

## Slide 17
Steps to develop an Action Plan
Step 2 - List tasks
Once you have your goal, list the tasks and activities you must complete to achieve it. Then order them sequentially by adding key dates and deadlines.
After setting the goals, it is time to prepare a list of tasks/action items to reach them.
Action items are small, individual tasks that must be executed to produce project deliverables that are outlined in your Action Plan.
First, you need to identify and define the tasks, and then assign them a priority level so that they’re executed sequentially.
Action items are tasks that should be executed to achieve a larger, more complex objective, such as an action plan or simply one of its pursued goals. Creating a list of action items is the most efficient way to assign these jobs to the proper agent and resources, and track their progress.
Action items may take many forms, from activities that must be completed to events that must take place. Their defining characteristic, though, is that each item completed leads to the conclusion of a greater task.
While they may appear simple, creating a list of action items is more important than you might expect. Poorly created action items lists can slow down an entire project or even lead to total failure. For this reason, it’s essential to understand the best ways to create action items and use them to propel your project forward.

## Slide 18
Steps to develop an Action Plan
Step 2 - List tasks
Once you have your goal, list the tasks and activities you must complete to achieve it. Then order them sequentially by adding key dates and deadlines.
Here are some steps to keep in mind when writing tasks/action items. The more detailed your action items, the more they’ll help facilitate workload management and the execution of your project plan.
1. Define a Title and ID Number for your Action Items
2. Assign a Priority Level (high to low priority) for the Action Items
3. Set deadlines for your Action Items
4. Assign an agent/responsible for your Action Items
5. Shortly describe Each Action Item

## Slide 19
Steps to develop an Action Plan
Step 3 - Prioritise tasks
Some action items may have to be completed before others can start. Prioritising these tasks and setting realistic deadlines can avoid blockings and allow action items to be executed sequentially. If you plan to assign them to team members, be sure to let them know the dependencies and allow them enough time to deliver them.
Now that you have a task list, it is time to reorganize it by prioritizing the action items. Some tasks you may need to prioritize as they can be blocking other subtasks.
You must assign each task and perhaps each subtask a priority of low, medium, or high, depending on how time-sensitive, how complex or time-consuming, and how critical that task is referring to the overall goal.

## Slide 20
Offline Activity 4.2
The main point of a Regional Action Plan is to produce a list of action items for the development of your region. In other words, drafting an Action Plan consists of listing the tasks each responsible needs to complete and prioritizing them, in order to achieve the established goal.
Offline Activity 4.1

## Slide 21
Steps to develop an Action Plan
After having your detailed list of prioritised tasks, you can start assigning them proper resources, time and team members, and decide if you will outsource any parts of the Action Plan.
Step 4 - Assign tasks
Resources
Your Action Plan requires some specific resources. After drafting your action item prioritised list , it will be easier to understand what resources you should assign to each task and distribute them accordingly.
Team members
After dividing the work required to accomplish your action plan in tasks/action items, you’ll need to assign them to your project team members and define their roles and responsibilities.
This step includes your budget assignment. You can indicate the approximate cost of each task in your Action Plan.

## Slide 22
Offline Activity 5
Now that you have specified the action items to be followed to achieve your Action Plan goal, you will need to assign the proper team members and resources to each of the tasks.

## Slide 23
Steps to develop an Action Plan
After completing each action item or task group, it is recommended to assess the ongoing progress and improve the Action Plan accordingly. Collect feedback from the action item responsible agents and improvement suggestions from them, to become more efficient in the execution of upcoming tasks.
Step 5 - Assess and improve
If you want to track your progress toward the Action Plan goal, you have to set a method to measure it. That would keep you and the task responsible agents up to date and motivated.
  You must establish metrics to measure your progress as well. Milestones could help divide long time periods into shorter and more easy-to-track periods.
To succeed in executing your Action Plan, you need to regularly monitor your progress. You can dedicate some time to assess the team performance.
Tasks can be marked as completed, focusing on how you have progressed towards the goal.
Assessing and monitoring could also allow you to analyse the delayed tasks, understand the reason of their delay and find solutions. After this analysis your team should update the Action Plan accordingly.

## Slide 24
Steps to develop an Action Plan
After completing each action item or task group, it is recommended to assess the ongoing progress and improve the Action Plan accordingly. Collect feedback from the action item responsible agents and improvement suggestions from them, to become more efficient in the execution of upcoming tasks.
Step 5 - Assess and improve
MILESTONES
A milestone is a tool that will allow you to divide a project schedule into smaller pieces.
Milestones allow you to monitor the progress by dividing the process and indicating the end of a group of action items and the beginning of a new one.
When a milestone focuses on big progress indicators, it helps identifying opportunities to improve the process, in order to better plan, schedule and execute the Action Plan.
Milestones are also an advantage to estimate the Action Plan’s required time by indicating and separating big relevant deliverables and progress indicators, which makes them a very useful tool for project managers.

## Slide 25
Offline Activity 6
Monitoring is useful to assess the progress of an Action Plan. By tracking your action items, you can compare actual to expected performance, and identify problems that can affect to the planned schedule and budget.
This also helps project managers and relevant stakeholders visualise the completed action items and the resources that have been used.

## Slide 26
Examples of Regional Development Action Plans I
The Regional Development Programme of Georgia is a medium-term government document setting out main goals in Georgia’s regional development and determining priorities and measures for the period 2018–2021.
The Programme provides a coherent framework for public and private investments promoting regional development, enabling all stakeholders to concentrate resources along a single, common strategy in order to maximise the effectiveness and efficiency of intervention.
Read more

## Slide 27
Examples of Regional Development Action Plans I
After an analysis of the situation, and exposing the goals and priorities of the Action Plan, each action item (measure) contains the following information:
Detailed explanation of the measure and activities
Related objectives
Budget
Output indicators
Result indicators
responsible agent (implementing body)
Read more

## Slide 28
Examples of Regional Development Action Plans II
Place and life in the ECE: A Regional Action Plan 2030 is a regional Action Plan for helping UNECE (United Nations Economic Commission for Europe) cities and national governments ensure simultaneous treatment of the multifaceted challenges to achieving sustainable and affordable housing and sustainable urban development.
It provides an integrated and balanced approach for supporting local and national development efforts until 2030 in two inter-linked policy areas: cities, neighbourhoods, homes and rural life; and sustainable housing and homes. It contains clear and concise guiding principles, goals, targets and actions for building more resilient, inclusive and sustainable people-centred cities in the UNECE region with affordable, accessible and climate-neutral housing.
Read more

## Slide 29
Examples of Regional Development Action Plans II
This Action Plan contains a very interesting distribution of the action items, according to their corresponding goal and specific objective.
Read more
Link to Action Plan file

## Slide 30
Examples of Regional Development Action Plans III
The REPLACE – Region of Crete Action Plan is a Regional Action Plan aiming to enable the transition to a circular economy by facilitating, implementing and financing local and cross-regional circular value chains using a systemic operational and normative framework.
Read more

## Slide 31
Examples of Regional Development Action Plans III
The action items in this Action Plan are described chronologically, according to their corresponding expected completion time.
Read more

## Slide 32
To find more Regional action Plans and good practices in regional development you can access:
https://projects2014-2020.interregeurope.eu/super/regional-action-plans/
https://www.interregeurope.eu/policy-solutions/good-practices/projects?keywords=&projects=SUPER-

## Slide 33
Offline Activity 7
Now that you are familiar with some regional Action Plans, you can work on a case study.

## Slide 34
Unit summary
What is an Action Plan?
An action plan is a list of action items and resources needed to achieve project goals and objectives.
Why do you need an Action Plan?
An Action Plan clarifies goals to be achieved, teams and service providers to involve, tasks, milestones, and resources needed to complete the project.
Goals
1- Define your goal
Steps to develop an Action Plan
Key elements of an Action Plan
2 - List tasks
3 - Prioritise tasks
4 - Assign tasks
5 - Assess and improve
Action items
Agents for each action item
Measures to evaluate progress
Resources for each action item

## Slide 35
Project Management Institute (2017). A Guide to the Project Management Body of Knowledge : (PMBOK guide). 6th ed. Newtown Square, Pa: Project Management Institute.
Bryson, J.M. (2018). Strategic Planning for Public and Nonprofit Organizations : For Public and Nonprofit Organizations, A Guide to Strengthening and Sustaining Organizational Achievement. 5th ed. Hoboken, Nj Wiley.
Kerzner, H. (2017). Project management: a Systems Approach to planning, scheduling, and Controlling. 12th ed. Hoboken, New Jersey: John Wiley & Sons, Inc.
Ivancevich, J. (2017). Organizational Behavior And Management. S.L.: Mcgraw-Hill Us Higher Ed.
Kerzner, H. (2017). Project management: a Systems Approach to planning, scheduling, and Controlling. 12th ed. Hoboken, New Jersey: John Wiley & Sons, Inc.
References

## Slide 36
Interreg Europe. (n.d.). Good practices. [online] Available at:
https://projects2014-2020.interregeurope.eu/super/good-practices/ [Accessed 13 Feb. 2023].
www.interregeurope.eu. (n.d.). Find policy solutions | Interreg Europe - Sharing solutions for better policy. [online] Available at:
https://www.interregeurope.eu/policy-solutions/good-practices/projects?keywords=&projects=SUPER [Accessed 13 Feb. 2023].
REPLACE – Region of Crete Action Plan. (2022). Available at:
https://projects2014-2020.interregeurope.eu/fileadmin/user_upload/tx_tevprojects/library/file_165 [Accessed 13 Feb. 2023].
Place and life in the ECE A Regional Action Plan 2030. (2022). Available at:
https://unece.org/sites/default/files/2022-07/Place%20and%20Life%20in%20the%20ECE_web_0.pdf [Accessed 13 Feb. 2023].
REGIONAL DEVELOPMENT PROGRAMME OF GEORGIA. (2018). Available at: https://policy.asiapacificenergy.org/sites/default/files/Regional%20Development%20Programme%20of%20Georgia%202018-2021%20%28EN%29.pdf [Accessed 13 Feb. 2023].
References

## Slide 37
Thank you!
@Regio.Digi.Hub